## 🗺 Story Map
Story Map Template by Avion.
🗺 Story Map | [5 empty] | 👥 View Personas
User Onboarding |  | Lobby & Setup |  |  | Game-Initialisation | In-Game |  | Post-Game
Welcome Screen | Account Selection | Creating a Lobby | Joining a Lobby | Lobby Management | Input Prompt | Countdowns | Drawing | Post Game Screen
↓ Sprint 1
Land onto a Welcome (Home) Screen. | View Account Management Screen with Login Options | View a Lobby type layout screen. | Enter/Paste the Lobby Code. | See who is in the Lobby. |  |  | View a drawing canvas.
|  | Copy Lobby Code to Clipboard |  | Option to start a game if minimum players have joined. |  |  | Be able to draw on the canvas.
Create an Account with a Username, Name and Password.
Login as a Registered Account.
↓ Sprint 2
| Select a Guest Account Option for Login. |  |  |  |  | View a countdown initiating the game. | View a tool selection box.
| Enter my name for my Guest Account. |  |  |  |  | View a countdown when drawing. | Select a Drawing Pen
| Login as a Guest. | [5 empty] | Select an Eraser
↓ Sprint 3
[5 empty] | Enter my own drawing prompt | View a countdown when prompting. | Select a Pen Colour | View all Drawings.
[5 empty] | Be notified that a player is entering a Prompt if it is not my turn to enter a Prompt. | View a countdown when guessing. | Select a Pen Size | View all Associated Prompts.
[5 empty] | Select a pre-listed prompt from a Random Set of prompts. |  | Be notified that a player is drawing/entering a Prompt. | Option to return to the Lobby screen for a New Game.
Option to End Lobby Session and return to Home Screen.
↓ Sprint 4
Accept/Decline Cookies. | When creating an account, safely assume that the information stored is securely stored. | Secure a Lobby session by setting a Password. | Enter a Lobby Password when joining if a Lobby if the Lobby requires one. |  |  |  | Select a Shape Tool which allows for basic shapes (Square, Circle, Rectangle). | Option to Export all Drawings and Prompts.
Select Lobby Name

## 👥 Personas
Avatar
Name | Muaawiyah Dadabhay | Muhammed Raees Dindar | Taahir Kolia | Irfaan Mia
Avatar Thumbnail